## Work Plan-2
|  |  | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Phases | Tasks | Status | 2014-02-10: Sprint 1; 2014-03-03: Sprint 2; 2014-03-24: Sprint 3; 2014-04-14: Sprint 4
Plan Project | Plan 1st sprint | Concluded | bar: 2014-02-10
| Plan 2nd sprint | Concluded | bar: 2014-03-03
Plan 3rd sprint | bar: 2014-03-24
Plan 4th sprint | bar: 2014-04-14
Explore Data | Extract Fifa Scores with python script | Concluded | bar: 2014-02-10
| Extract Fifa Ranking with python script | Concluded | bar: 2014-02-10 to 2014-02-17
Check correlation - proportion of wins vs game location (home/away) by drafting graphs in Excel | bar: 2014-03-10 to 2014-03-17
Check correlation - proportion of wins vs opponents position/distance in fifa ranking by drafting graphs in Excel | bar: 2014-03-10 to 2014-03-17
Check correlation - proportion of wins vs historical results by drafting graphs in Excel | bar: 2014-03-10 to 2014-03-17
Define Predicting Model | Define model | bar: 2014-03-17
Train model | bar: 2014-03-24
Test model | bar: 2014-03-24
Design Blog Post | Design blog post | bar: 2014-03-24
Develop blog post draft (in D3js) | bar: 2014-03-31 to 2014-04-07
Test blog post draft (have some external audience criticize it) | bar: 2014-04-07
Develop Blog Post | Refine blog post | bar: 2014-04-14 to 2014-04-21
Test blog post (have some external audience criticize it) | bar: 2014-04-21
Deploy blog post | bar: 2014-04-28
Celebrate!

## Work Plan-1
|  |  |  | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Phases | Tasks | Member | Status | 2014-02-10: Sprint 1; 2014-03-03: Sprint 2; 2014-03-24: Sprint 3; 2014-04-14: Sprint 4
Plan Project | Plan 1st sprint | Andrew | bar: 2014-02-10
| Plan 2nd sprint | Shiya | bar: 2014-03-03
| Plan 3rd sprint | Andrew | bar: 2014-03-24
| Plan 4th sprint | Shiya | bar: 2014-04-14
Explore Data | Extract Fifa Scores | Andrew | bar: 2014-02-10
| Extract Fifa Ranking | Shiya | bar: 2014-02-10 to 2014-02-17
| Explore game scores | Andrew | bar: 2014-02-17
| Explore team rankings | Shiya | bar: 2014-02-17
| Draft scores graphs (in Excel or other tool) | Andrew | bar: 2014-02-17 to 2014-02-24
| Draft ranking graphs (in Excel or other tool) | Shiya | bar: 2014-02-17 to 2014-02-24
Define Predicting Model | Define model | Andrew | bar: 2014-03-03 to 2014-03-10
Shiya | bar: 2014-03-03 to 2014-03-10
| Train model | Andrew | bar: 2014-03-10
Shiya | bar: 2014-03-10
| Test model | Andrew | bar: 2014-03-17
Shiya | bar: 2014-03-17
Design Blog Post | Design blog post | Andrew | bar: 2014-03-24
Shiya | bar: 2014-03-24
| Develop blog post draft (in D3js) | Andrew | bar: 2014-03-31 to 2014-04-07
Shiya | bar: 2014-03-31 to 2014-04-07
| Test blog post draft (have some external audience criticize it) | Andrew | bar: 2014-04-07
Shiya | bar: 2014-04-07
Develop Blog Post | Refine blog post | Andrew | bar: 2014-04-14 to 2014-04-21
Shiya | bar: 2014-04-14 to 2014-04-21
| Test blog post (have some external audience criticize it) | Andrew | bar: 2014-04-21
Shiya | bar: 2014-04-21
| Deploy blog post | Andrew | bar: 2014-04-28
Shiya | bar: 2014-04-28
Celebrate!